## Slide 1: NASA Update
NDIA PMSC Quarterly Meeting
August 26, 2010
Ken Poole
NASA/MSFC/CS40 (Project Planning & Analysis Team)
256-544-2419

## Slide 2: Topics
1. Policy and Requirements Update
3. EVM Capability Development Summary Schedule
2. NASA EVM Capability Development Status

## Slide 3
NASA’s Program/Project Management Requirements for Flight Projects, NPR 7120.5 version E is still on track for a 4th Qtr CY2010 completion
  Provides additional guidance and clarity to Project Planning & Control requirements
    Applicability of ANSI/EIA-748 guidelines vs. EVM principles for NASA in-house projects with a life cycle cost of estimate of greater than $20M
    IBR requirements for NASA in-house project implementations
    Ensure consistency between new “Management Agreement” definition and PBB (Includes PMB & Reserves)
    Initiate EVM planning during project Formulation (phases A & B) with formal application and reporting starting in project Implementation (phase C)
    Acknowledges and requires adequate cost and schedule margin to be incorporated into the project integrated baseline
Completed Revision 4 of our draft Agency EVM System Description document (end of July). Further updates to come based on findings & results of our continued EVM project pilot testing
Policy and Requirements Update

## Slide 4
NASA EVM Capability Development Status
Findings and comments from an Independent Peer Review of our Draft NASA EVM System Description & other associated documents have been assessed and adjudicated.
Updates to the EVM System Description resulting from Peer Review have been incorporated and a new draft revision was completed. Updates to associated documents (handbooks and training) are scheduled.
  First EVM project pilot was brought to a premature completion due to the impacts and changes resulting from the cancellation of the Constellation Program. (Extra Vehicular Activity (EVA) Project at JSC). Insights and benefits were gained even though the pilot testing was shortened:
  Typical implementation gaps were identified and better understood
  Over 50 Lessons Learned were documented for use in helping to better define our Agency EVM documentation, guidance, and methods
  Gained insights into potential process work-arounds for problem areas

## Slide 5
NASA EVM Capability Development Status
  Started the second of two EVM pilot projects this month in which we will further test and validate our proposed Agency EVM processes and products. (Ice, Cloud, and land Elevation Satellite II (ICESatII) Project at GSFC). (The ICESatII project is currently in Phase A Formulation with no preliminary baseline established yet. This project contains a significant amount of in-house development along with prime contracted effort allowing us to also test how we best merge all EVM data for a total project picture.)
  Update EVM process training material for pilot project use and later Agency-wide use – (October 2010)
  Draft update of the NASA EVM Implementation Handbook – (September 2010)
  Draft update of the NASA CAM Handbook for EVM – (September 2010)

## Slide 6
EVM Capability Development Summary Schedule