## EVM Health Scorecard
Program | EVM Contract Requirements | Baseline Development/IBR/Maintenance | Analysis/ Integration | EV Management Systems | DCMA | Training
Program A | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Program B | GREEN | GREEN | YELLOW | YELLOW | YELLOW | YELLOW
Program C | YELLOW | YELLOW | YELLOW | YELLOW | GREEN | GREEN
Program D | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Program E | YELLOW | YELLOW | GREEN | GREEN | YELLOW | GREEN
Program F | GREEN | GREEN | GREEN | YELLOW | GREEN | GREEN
Program G | GREEN | GREEN | GREEN | GREEN | YELLOW | GREEN
Program H | GREEN | GREEN | GREEN | YELLOW | YELLOW | GREEN
Program I | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Program J | GREEN | GREEN | GREEN (BP) | GREEN | GREEN | GREEN
Program K | GREEN | GREEN | GREEN | YELLOW | GREEN | GREEN
Program L | GREEN | GREEN | GREEN | GREEN | GREEN (BP) | GREEN
Program M | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Explanations below for all: GREEN - Best Practices (BP); Green with downward trend; YELLOW; and RED areas.
Program B | Y | Analysis / Integration: CFSR does not reconcile with CPR. Scheduling analysis cannot be effectively conducted without an Integrated Master Schedule (IMS).
| Y | EV Management Systems: Contractor does not have an Integrated Master Schedule (IMS).
| Y | DCMA: Follow up is in progress on contractor EVMS schedule integration issues.
| Y | Training: Contractor is going through additional training on in-house EVM tools i.e., Open Plan scheduling system to effectively discuss and provide schedules to the customer.
Program C | Y | EVM Contract Requirements: Program is in the process of applying EVMS on a significant amount of future work per contractor's EVM System. This will ensure government has the anticipated visibility into status of contract execution.
| Y | Baseline Development/ IBR/ Maintenance: DCMA issued Level 3 Corrective Action Report (CAR) May 07 for not planning CLIN’s 1 and 5 for Long Lead Material.
| Y | Analysis / Integration: Program has made a commitment to assess / reduce the high % of LOE on a significant amount of future work thus facilitating program visibility via objective (discrete) performance measures.
| Y | EV Management Systems: A DCMA-conducted EVM Compliance Review found that contractor is neither following nor consistently applying their EVM System in accordance with the EVMS Guidelines.
Program E | Y | Baseline Development / IBR / Maintenance: IBR conducted in Mar 07. Pending the verification during the next IBR that contractor's planning /scheduling integration issues have been addressed and baseline change procedures are being applied, this area remains Yellow. Since the new contract Period of Performance begins 1 Jan 08, the program is planning to conduct the next IBR on that work in early CY 08.
| Y | DCMA: Program does not have an MOA with DCMA and therefore does not benefit from DCMA/contractor EVMS Joint Surveillance Process.
FBX-T |  | Analysis/Integration:
| Y | EVM Contract Requirements: Program did not implement complete and correct EVM requirements on new contract as required by DoD and MDA policy.
Program F | Y | EV Management Systems: A DCMA-conducted EVM Compliance Review found that contractor is neither following nor consistently applying their EVM System in accordance with the EVMS Guidelines. DCMA will conduct a follow-on EVM Compliance Review in late Mar 08.
Program G | Y | DCMA: There is no MOA for DCMA support on the program.
Program H | Y | EV Management Systems: A DCMA-conducted EVM Compliance Review found that contractor is neither following nor consistently applying their EVM System in accordance with the EVMS Guidelines.
| Y | DCMA: There is no MOA with DCMA.
Program J | G (BP) | Analysis / Integration: Program CPR Format 5 provides an excellent financial overview, program accomplishments; baseline changes (BCRs) as well as variance analysis which enable the government to do trend/EAC analysis.
Program K | Y | EV Management Systems: Program has not implemented an EVMS as they previously committed to. Based on an EVM System Surveillance Review in Dec 07, it appears there is no longer a commitment to do so.
Program L | G (BP) | DCMA: Excellent MOA, use of DCMA, and Scorecard process
Aegis AWS
Aegis SM3
ABL
ABL