## Slide 1
Program Management Systems Committee (PMSC)
Contract / Subcontract Issues Working Group
26 August 2010
Mike Martin

## Slide 2: Joint Team Members
Mike Martin – Pratt & Whitney / UTC (Lead)
Gay Infanti – Northrop Grumman
Peter Schwarz – MDA
Jeff Poulson – Raytheon
Adam Duncan - Raytheon
Mike Pelkey – OSD DPAP
Randy Steeno – Boeing
TBD – OSD PSA
TBD – DCMA EV Center
TDD – OSD PARCA
Dan Feeney – Lockheed Martin
Kathryn Flannigan – General Dynamics
Tom Tasker – General Atomics
Mike Pauly – ITT
Barbara Kjorstad – ATK
Gil Kjorstad – ATK

## Slide 3: Overview
The actions contained herein have or will be executed through a collaborative industry / government effort
The team is currently reenergizing its efforts but still awaiting some key government participants.
The following issues remain unresolved:
  Contract vs. EVM system order of precedence
  Subcontractor validation
  Subcontractor Surveillance compliance and surveillance
  EVM Implementation Challenges
  Use of a supplier’s previously-validated process at a new supplier site
  DCMA EV Standard Surveillance Instruction (SSI)
  Ownership and Control of Management Reserve
  Undefinitized Contractual Actions (UCAs) / Unpriced Change Orders (UCOs)
  Treatment of existing CAR’s when Business Systems DFARS is implemented.
Notes: Removed from chart:

## Slide 4: Order of Precedence
In addition to including FAR or DFARS EVMS clauses on contracts, contracting officers frequently include other provisions that often require suppliers to modify or depart from their standard, validated EVM Systems to manage their contracts and meet the requirements of their contracts. These provisions may be found in sections of the contract that take precedence over Section I, where the EVMS clauses are contained, e.g.,
  Section H – Special Provisions
  Section C – Statement of Work requirements
.
Previously DCMA’s stated policy is to issue Corrective Action Request (s) against the contractor for following contract direction.
Issue
Team Position
Contractors are obligated to follow the contracts.
In the sprit of cooperation the Contractor and the cognizant CMO should notify the PCO of any conflicting requirements.
The DCMA, CMO and the PCO should reach a solution with the government PM which precludes noncompliance with either the ANSI or the contractor’s validated EVMS.
Previous DCMA Director concurred and verbally instructed the EVM Center to use 1716 process rather than issuing CARs to suppliers for findings of non-compliance arising from contractual provisions.
Actions Pending
Suggest readdressing this issue with PARCA and DCMA EVM Center.
Document the process in the EVMIG.

## Slide 5: Subcontractor EVMS Validation
Issue
Previously a subcontractor had the ability to request one of three options when required to have a validated EVMS; the EVMIG and other guidance documents vested primary responsibility in the prime contractor.
  Prime Contractor Review Only
  DCMA Review Only (at sub’s request)
  DCMA and Prime Contractor Review
October 2006, DCMA revised the EVMIG to assign DCMA sole responsibility for subcontractor validation.
  DCMA has no privity of contract with subcontractor
  Prime retains responsibility for subcontractor’s performance but has no authority or control over validation review
  EVMIG change also precludes recognition of acceptance by other agencies or primes (reciprocity).
Industry Position
EVMIG change/inconsistencies will likely result in need for dual industry processes for subcontractor validation (for DOD and non-DOD contracts).
Prime contractors should be required participants in subcontractor validation reviews since they retain responsibility for
  Subcontractor performance
  Accuracy and fidelity of CPRs, including reported subcontractor data
  Prime contractors are being held responsible for subcontractor EVMS (some primes received CARs for subcontractor failure of validation and/or compliance reviews).
Actions Pending
Include this issue with current Subcontracting Teaming Issue under consideration by PARCA. Clarify DOD policy / guidance with PARCA and the EVM Center.
Industry/Government collaboratively update the EVMIG and Compliance Review Instruction (CRI) to clarify roles and responsibilities.

## Slide 6: Subcontractor Compliance and Surveillance
Issue
Previously a subcontractor had two options for surveillance of subcontractor EVMS
  Prime Contractor Review Only
  Assist audit by cognizant local DCMA CMO
EVMIG revised to assign responsibility for subcontractor EVMS surveillance to DCMA
However, some primes receiving CARs for failing to perform subcontractor EVMS surveillance as part of their subcontract management responsibilities
Industry Position
Industry proposed solution:
Ensure Prime CMO delegates EVM Surveillance responsibility via “Letter of Delegation” to ensure annual surveillance is conducted. Prime may attend if there is no competitively-sensitive data.
Local DCMA CMO assigned to perform the assist audit should
  Notify the prime and invite the prime’s participation in the surveillance review, where possible, i.e., limited to review of non-sensitive data)
  Report surveillance findings and corrective action plans to the prime contractor
Include the following as an option within the EVMIG if the initial actions do not succeed: Delegate the responsibility for subcontractor surveillance to prime contractors since primes retain responsibility for
  Subcontractor performance
  Accuracy and fidelity of CPRs, including reported subcontractor data
Include this issue with current Subcontracting Teaming Issue under consideration by PARCA. Clarify DOD policy / guidance with PARCA and the EVM Center.

## Slide 7: EVM Implementation Challenges
Evidence that EVM and Contracting experts are not collaborating, via IPTs, on the contractual application and use of EVMS during acquisition planning.
Evidence of this is as follows:
  Incorrect flow down and/or omission of EVM contractual requirements.
  Improper contract direction forcing the contractor or subcontractor to violate their approved system.
  Over / Under application of EVM requirements
  Improper application of requirements for follow on options
  Improper use of Management Reserve (MR)
  Integrated Baseline Review (IBR) timing
  Inappropriate application to Contract Type and/or Work Content
Root Cause needs to be identified and worked to closure.
Issue
Team Position
NDIA PMSC should establish an Industry / Government team to generate a training package which can be delivered to all federal agencies and contractor organizations.
Actions Complete
D. Tomsic developed/delivered training on 7/29/08 through NCMA audio seminar.
OSD issued correspondence including “EVM Contract Requirements Checklist” to all commands.
DPAP correspondence “EVM Requirements and Reporting” issued 8/27/08 Memo addresses this item and references checklist with link to web site to obtain current version.
Actions Pending
DoD DST sub team has completed their assignment. Request Debrief from OSD.
There are still an issues within our community.
Help is needed from Government team members to alleviate these escapes.

## Slide 8
Issue
Standard Surveillance Instruction (SSI)
DCMA EV Standard Surveillance Plan (SSP) implemented throughout the agency without being distributed to industry for comment.
Issues include but are not limited to:
Review and adjudication of all CARs by the EV Center; lack of defined dispute process.
Risk Based Surveillance approach not adequately tied in with surveillance planning and execution.
Lack of coordination of surveillance findings among supplier sites using same EVMS.
Increased level of detail and amount of data requests to support surveillance.
Relationship of NDIA Intent Guide to the surveillance.
Need for surveillance process cycle time improvements (esp. response times).
Existing AA provisions that require ACO notification rather than DCMA EVMC approval prior to implementation.
Team Position
NDIA PMSC working with DCMA to achieve a timely review and closure on any areas of concern
DCMA agreed to break out separate small group of Industry and Government participants to review the process and make recommendations for improvement
Industry Representatives
Boeing : Randy Steeno
Lockheed Martin: Pete Wynne
Northrop Grumman: Gay Infanti
Raytheon: Jeff Poulson
Pratt & Whitney: Mike Martin
DCMA EV Center: Donna Holden, Kelli Coon
Schedule
01/09: Industry Comments to DCMA
Jan – August 2009: Joint Team Meetings
September ‘09:Draft approved through EVMC
April ’10: Industry Face to Face with EVMC
May – August ‘10: Update and reformat document in accordance with new agency instructions. Includes all accepted industry comments and agency changes due to reorganization and other considerations.
September – October ’10: DCMA Management Review
November – December ’10: Document Release

## Slide 9
Issue
Application of Existing Validation to Another Company Site
Many suppliers utilize accepted EVM systems, e.g., corporate, sector or division-level EVM Systems, at multiple sites.
Can a previously accepted EVMS be applied to a new site without the need for re-validation by DCMA?
Team Position
Verify compliance at the new site through via annual surveillance.
Accumulation of Cage Codes by DCMA is now in process.
EVMIG does not address site specific acceptance.
Industry/Government collaboratively update the EVMIG and Compliance Review Instruction (CRI) to clarify roles and responsibilities.
Clarify DOD policy / guidance with PARCA and the EVM Center.

## Slide 10
Issue
Ownership and Control of Management Reserve
Contractors have been directed by government program managers and contracting officers and by prime contractor program managers to use Management Reserve (MR) for purposes other than the intent expressed in Guideline 14 of the ANSI/EIA-748 Guidelines, the NDIA ANSI/EIA-748 Intent Guide, validated EVM system descriptions and long accepted best practices. Examples of this questionable direction are coverage of out-of-scope work and to cover overruns.
Team Position
Draft position paper has been established.
Review position paper with PMSC Board to obtain approval and guidance on the proper communication vehicle.

## Slide 11
Issue
Undefinitized Contractual Actions (UCA’s) & Unpriced Change Orders (UCOs)
Undefinitzed Contractual Actions (UCA’s) and Unpriced Change Orders (UCO’s) have been creating unnecessary program administrative cost and/or preventing the initiation of contractual effort.
  - The negotiation process is too lengthy causing PMB instability due to the incremental work release and associated replanning and budgeting effort.
Team Position
Team to review new DFARS Clause prior to draft of position paper.
Team to establish position paper for communication with senior DOD Officials.
Review position paper with PMSC Board to obtain approval and guidance on the proper communication vehicle.

## Slide 12
12
Issue
Treatment of existing CAR’s when Business Systems DFARS is implemented
Currently there are hundreds of open CARs within the DCMA system.
How is DCMA and DCAA going to treat the existing CARs which were written prior to Business Systems DFARS clause enactment?
Team Position
Industry suggests that DCMA provide the list of all CAR’s to each company EVMS focal point for analysis and to ensure any further actions needed to ensure timely closure are taken.
With the advent of the Business Systems DFARS Clause accuracy of CAR and Corrective Action Plan Status is critical.
Assign DCMA and Industry focal points in each contractor location to ensure accuracy of CAR and CAP status.
Team suggests Senior DOD and Industry Leadership meeting be held when Business Systems DFARS is Implemented. Purpose is to communicate the process for system withdrawal and withholds.

## Slide 13: Summary
The following issues remain open pending further actions:
  Contract vs. EVM system order of precedence.
  Subcontractor compliance, validation and surveillance.
  EVMS Implementation Challenges.
The following issue is actively being worked to closure in 2010.
  DCMA EV Standard Surveillance Instruction (SSI)
The following issues are relatively new and need full team discussion:
  Use of a supplier’s previously-validated process at a new site.
  Ownership and Control of Management Reserve.
  Undefinitzed Contractual Actions (UCA’s) & Unpriced Change Orders (UCOs)
  Treatment of existing CAR’s when Business Systems DFARS is implemented.
Once new government participants are established suggest a face to face kickoff to reenergize the team.